## Sheet1
Week | <component> | Start | End | Status
2021-01-03 | Continuous Integration Setup | 2021-01-03 |  | In Progress
2021-01-10 | Continuous Delivery on Azure
2021-01-17 | Documentation of Work
2021-01-24 | Demo of Work for Submission
2021-01-31 | Review Feedback and do corrective actions based on Feedback
2021-02-07 | Project Clean up
| Goals | Goals
Continuous Integration Setup
Set Up Azure Cloud Shell
Create the Cloud-Based Development Environment
Create Project Scaffolding
Local Test
Configure GitHub Actions
Enable Github Actions
Modify Github Actions yml code
Verify Remote Tests pass
Screen Shot and update README.md
Continuous Delivery on Azure
Continuous Delivery on Azure
Add Flask Started Code to project
Enable Continuous deployment using Azure pipelines
Screen Shot and update README.md
Documentation of Work
Document Work in Github
update project plan
update Trelo board
Create Architecture Diagram
Instructions to run the application
Demo of Work for Submission
Visual Demo of Project
Create Quicktime video of project
Upload to Youtube and get feedback from a friend
Make final changes and update project README
Review Feedback and do corrective actions based on Feedback
Project Review Feedback
Project Clean up
Clean up Azure Resources
Delete pipeline
Delete azure app